Hellenic Ministry of Education and Religious Affairs, Culture and Sports

41 Ethnikis Antistaseos Avenue, 142 34 Nea Ionia, Athens, Greece

Athens, 20 November 2012

Ref No.:	Δ/21885

CALL FOR PROPOSALS

Concerning the submission of proposals for the conclusion of a service contract under private law

for the provision of services in the framework of the Action
“Development of the National Qualifications Framework (NQF)”

(Sub-project 1 “Development of methodological tools” and Sub-project 2 “Classification of qualifications in the NQF and their correspondence according to the European Qualifications Framework”)

CO-FINANCED BY THE EUROPEAN SOCIAL FUND

The National Organisation for the Certification of Qualifications and Vocational Guidance” (EOPPEP), intends to award  a service contract with an Expert with international experience (IE.1), for the provision of services in the framework of the approved proposal for the “Development of the National Qualifications Framework”.

The project under the title of “Development of the National Qualifications Framework” is an horizontal action of the Operational Programme “Human Resources Development” and will be co - financed by the European Social Fund (ESF) as well as by National Funds. The intermediate competent Project Management Authority is the competent Management Unit of the Operational Programme “Education and Life Long Learning” of the Ministry of Education and Religious Affairs, Culture and Sports.

Specifically, the project concerns the implementation of Sub-project 1 entitled “Development of methodological tools” and Sub-project 2 titled “Classification of qualifications in the NQF and their Reference to the European Qualifications Framework”.

In this respect, the interested parties are invited to submit Proposals, in accordance with the present Call.

1. LEGAL FRAMEWORK OF THE CALL FOR PROPOSALS

The call for proposals will be conducted in accordance with the relevant legislation and specifically according to the following provisions:

-The EOPPEP application / file with reference number EOPPEP 12281/31-7-2012 addressed to the Special Managing Authority of the Operational Programme of Education and Life-Long Learning for the issuance of operational competency.

-The operational competency document under reference number 18675/2012 addressed to EOPPEP as at 21/9/2012.

-The Induction Decision under reference number 12733/3.8.2012 of the Horizontal Act “DEVELOPMENT OF THE NATIONAL QUALIFICATIONS FRAMEWORK” under the Operational Programme “Human Resources Development”.

-Law 2621/1998 (Government Gazette Α 136), article 23 paragraph 2, as amended by article nine, paragraph 23 Law 4057/2012 (Government Gazette A 54), as reinstated by article 10 N. 4076/2012 (Government Gazette A 159), as amended by paragraph 11 of article 58, Law 4009/2011 (Government Gazette A 195).

-Law 2527/1997 (Government Gazette Α 206), article 6, as amended an in force.

-Law 4071/2012 (Government Gazette Α 85), article 44 paragraph 5 section b) aa.

-Law 3812/2009 (Government Gazette Α 234), article 10.

-Law 3614/2007 (Government Gazette Α 267), “Management, control and implementation of development interventions for the programming period 2007-2013”.

-Law 3861/2010 (Government Gazette Α 112), article 2 paragraph 4.

2. BRIEF DESCRIPTION OF ACTION

The objective of this project is the development of the Hellenic National Qualifications Framework. EOPPEP will develop the mechanism that will record the qualifications (awards) of formal, non-formal and informal education and will establish the National Qualifications Framework. The aim is to classify the qualifications in the National Qualifications Framework levels and to reference them to the eight levels of the European Qualifications Framework.

3. PROJECT

In the context of Sub-project 1, the International Expert (IE.1) will provide the following services:

- Development of the NQF’s level descriptors.

- Design and development of qualifications ‘types’.

- Develop methodologies for the inclusion of all Greek qualifications into NQF and their reference to the European Qualifications Framework.

- Transfer their know-how and expertise to the EOPPEP staff and other interested parties in relation to the above mentioned issues via seminars and workshops.

In the context of Sub-project 2, the International Expert (IE.1) will provide the following services:

- Support in the Reference of the Hellenic National Qualifications Framework to the European Qualifications Framework.

The following table illustrates a) the project’s deliverables, b) the project’s duration, c) the required inputs in man/months and d) the contractual budget.

| Objectives of the Contract- Deliverables | Sub-project | Duration | Inputs in man months | Budget (€) |
| --- | --- | --- | --- | --- |
| Methodology for the development of level descriptors (Levels 1-5) and ‘types’ of qualifications | 1 | 1/12/12-31/7/13 | 4.5 | 40,375.00 |
| Methodology for classifying / referencing qualifications |  |  |  |  |
| Design and delivery of Seminar(s) |  |  |  |  |
| Support to the Referencing process of the Hellenic NQF to EQF | 2 |  |  | 2,375.00 |
| TOTAL |  |  |  | 42,750.00 |

Explicitly is declared the prohibition of assignment of the project to others. EOPPEP reserves the right to extend the duration of the project.

It should be noted that the expert’s contractual obligations include his/her cooperation with other experts as well as EOPPEP staff involved in the Project and his/her participation in meetings for the optimum coordination of the services provided.

Travel and part of accommodation expenses will be reimbursed by EOPPEP. (Category “direct expenses” of the approved Action).

4. Monitoring Project Implementation – Approval of Deliverables and of the Project

The competent body for monitoring the implementation of the contract and its good performance as well as for the approval of the Experts’ deliverables and the project is the Monitoring Committee of the Sub-Project, which will be established by decision of the EOPPEP Board of Directors.

The deadline for submission of deliverables and consequently their approval by the Steering Committee shall be determined in the respective contracts to be signed with the Expert.

5. INTELLECTUAL PROPERTY

All the deliverables, data and every other documents or file related to the project that shall be acquired, accumulated, prepared and developed by the contractor during the performance of the contract, with funds from the Project, shall be confidential and belong exclusively to the beneficiary body (EOPPEP), who is solely responsible for its management and operation. EOPPEP has the right to add, amend, dispose of, or use this property in any other manner without prior approval by the contractor, or any other third party involved in its production or performance. All of the project’s intellectual rights belong to the beneficiary body (EOPPEP). It is explicitly agreed within the contract that the contractor shall transfer all the project’s intellectual property rights to the beneficiary body (EOPPEP), which will be the project’s exclusive beneficiary, having all the authorities deriving from it. In respect of other issues, the provisions of Law 2121/1993 regarding intellectual property shall apply.

6. REMUNERATION – PAYMENT METHOD

The Contract value appears in Table 1. EOPPEP is not required to pay any insurance contributions for the expert.

The remuneration of the expert will be paid in equal amounts upon approval of each deliverable.

In order for the remuneration to be paid, the expert should submit the required supporting documents. The expert’s payments may depend on the NSRF cash flow.

7. SUBMISSION OF PROPOSALS

The candidates have to submit their proposals and the required supporting documentation as mentioned in the points below, to the following address: EOPPEP, 41 Ethnikis Antistaseos Ave., N.Ionia Attikis P.C. 14234, Greece.

The deadline for submission of the expressions of interest is 18/12/2012, 12.00.pm.

The proposal and supporting documentation shall be sent by mail in a sealed envelope, either by registered mail, or by courier, with the sender’s details and the following indication being clearly stated:

Proposal for the Project “Development of a National Qualifications Framework” International Expert (IE.1)

The proposals and the required supporting documents must be submitted in English.

The following will not be taken into account:

- Proposals that are submitted in any manner other than the aforementioned.

- Proposals which have not used the template attached.

- Proposals whose supporting documentation is incomplete, as stated in the following points (9).

- Proposals that are submitted after the deadline.

The summary of this Call for Proposals will be published on the EOPPEP website (www.eoppep.gr), Special Management Unit of the Operational Programme of Education and Lifelong Learning website (www.edull.gr) and the Cedefop website (www.cedefop.europa.eu/EN) and pursuant to the provisions of Law 3861/2010, it will also be published on the www.diavgeia.gov.gr website.

Information in relation to the submission of proposals shall be provided by the EOPPEP Directorate for the “Accreditation of Qualifications” at the following phone numbers 0030 210 2709106.

8.  FORMAL REQUIREMENTS

NECESSARY QUALIFICATIONS

- University degree

- 4 years of experience at European or international level in the development of a National Qualifications Framework

- Fluency in English (speaking, writing)

ADDITIONAL QUALIFICATIONS

- Post-graduate degree in education

- Additional, vocational experience with regard to the development of National Qualification Frameworks exceeding four (4) years.

- Experience in issues concerning  NQF level descriptors development

- Experience in qualifications -types development

- Expertise in the development and operation of the European Qualification Framework (EQF)

- Experience in the development of policies and criteria for the classification of qualifications in the National Qualifications Framework and the reference of the qualifications to the European Qualification Framework.

- Experience in preparing NQF Referencing Reports.

9. SUPPORTING DOCUMENTATION

Under penalty of exclusion, the candidates must submit the following to EOPPEP:

- The completed “Proposals for contract template” form.

- Photocopies of their University degrees.

- Curriculum vitae.

- Certificates or other official documents from their employers which state precisely the duration and the type of service (experience); the employer’s details, or any other official document proving their employment and/or certificates of insurance institution which show the insurance period (as a proof of professional experience).

The candidates may submit additional evidence supporting their proposal.

10. EVALUATION OF PROPOSALS - SELECTION

The evaluation of proposals that will be submitted within the deadline will be evaluated by an Evaluation Committee, which shall be determined by decision of the EOPPEP Board of Directors. The evaluation procedure includes:

- The evaluation of the proposals pursuant to the above, as defined in point 9.

- Assessment and evaluation of the qualifications.

- The EOPPEP Board of Directors’ recommendation for the approval of the results.

The Evaluation Committee is entitled, if it deems this necessary, to request clarifications from the recommended candidate in relation to his/her proposal (e.g. degrees and professional experience, scientific specialisation and professional capacity that he/she has in order to implement the project). In this case, the clarifications are mandatory for the recommended candidate and are not considered as a counter-proposal.

The evaluation of the candidates is based on the graded Evaluation Grid below:

| S/N | Evaluation Criteria | Maximum points |
| --- | --- | --- |
|  | University degree | 5 |
|  | 4-years of professional experience at European or international level in the development of National Qualifications Framework | 5 |
|  | Post-graduate degree in education | 5 |
|  | Additional, vocational experience with regard to the development of national qualification frameworks exceeding four (4) years. | 35 |
|  | Experience in issues concerning NQF level descriptors and qualifications-types development | 15 |
|  | Expertise in European Qualification Framework (EQF) development and operation | 10 |
|  | Experience in the development of policies and criteria for the classification of awards in the National Qualifications Framework (NQF) and their reference to the European Qualification Framework | 10 |
|  | Experience in preparing EQF Referencing Reports | 15 |
|  |  | 100 |

The results of this procedure will be published on the EOPPEP website.

Contract summaries that will be prepared following the expert’s selection will be published on the EOPPEP and Diavgeia websites.

EOPPEP reserves the right to cancel the present call.

EOPPEP may recall the validity of part, or all of this call for proposals. The notification of such revocation shall be posted on its website.

KONSTANTINOS KALTSAS

Chairman of the EOPPEP BoD